## Contents
Contents
Introduction
1) Strategy and Finance
2) Legal & governance
3) Operational
4) Students
5) Academic Delivery
6) Staff and HR
Appendices
Last updated: 15/07/2025 © Southern Universities Management Services 2025

## Introduction
#VALUE!
Introduction This framework is a distillation of the key lessons learnt from the SUMS and OIAHE study on Putting students first: Managing the impact of higher education provider closure (July 2025). It is not intended as a comprehensive guide for good institutional governance or achieving financial sustainability. The framework provides a checklist of key actions that might be taken by Higher Education Providers (HEPs) to mitigate the risk of market exit and, if exit is undesirable or unavoidable, to help manage an exit. The framework focuses on what should be done, not how to do it. The framework is not intended as a definitive list of actions but a prompt for HEPs to support and inform their planning. Closure and market exit is typically more complex and financially challenging for HEPs than for commercial organisations for numerous reasons including: • The need to potentially continue to support students for several years • The difficulty in finding alternative course providers; especially in regions where there are few providers • HEPs’ multiple sources of funding, including from government • HEPs' participation in HE and other public sector pension schemes • Students not being prioritised by insolvency legislation but treated as unsecured creditors. Our framework drives committed engagement with and holistic support for students, transparency and informed decision making.
While each provider will face different challenges and timelines for action, depending upon their context, underperforming HEPs may swiftly follow the demise curve as illustrated. Our framework focuses upon waves one to four: from normal operations, through the emergence of warning signs and contingency planning (including consideration of new strategic pathways), to preparing for market exit. The duration for each wave will vary by provider. Timelines will be influenced by several factors including how early warning signs emerge and/or the criticality of issues. Consideration of options and instigation of new strategic pathways will take time that may not be available; for example, a merger may take up a year or more to organise. The aim should be to have sufficient time to explore options and to be able to make well informed timely decisions. Actions taken may result in stabilisation and recovery or in a market exit. Typically, a HEP will move through waves of activity. The process will not be clearly defined and linear. There will be some overlapping of activity and occasions of iteration. Some institutions have described the exit process as a chaotic storm. The waves of activity as set-out seek to simplify the process by setting out a high-level road map.
#VALUE!
The framework focuses upon prevention and management of a market exit during Waves 1 to 4. Wave 1 Normal operations - the institution is operating in a stable state before warning signs of serious problems begin to emerge Wave 2 Warning signs begin to emerge - serious issues are identified that may if not addressed necessitate a market exit. Wave 3 Contingency planning - options to mitigate the risk of exit are explored and contingency plans are made, for example, financial restructuring is undertaken and/or new strategic pathways are instigated, for example, merger. Wave 4 Preparing for market exit - the need to exit the market has been formally recognised by the HEP. It is during this Wave that plans for exit begin to be made. Actions taken and plans made during this Wave will be critical for a successful and orderly market exit. Wave 5 Market exit – exit is happening and the plans created in wave 4 will be put into place. If necessary, administrators/liquidators will be appointed who will take control of the HEP. If an Administrator is appointed, they will have a very wide range of powers that must be used for the benefit of the creditors. They will typically use the plans created in Wave 4 by the HEP, if they consider them appropriate. The framework is separated into sections that reflect spans of responsibilities with HEPs: Strategy and Finance, Legal and governance, Operational, Students, Academic Delivery and Staff and HR. For the purposes of this framework, we have made several overarching assumptions: • HEP is in a mature state of organisational development, i.e. it is not a start-up • HEP will have complied with the Office for Students' (OfS) conditions of registration that are intended to ensure that students can continue their studies or receive appropriate compensation (Condition 3 and Condition 4 specifically) OfS interventions are out of scope for the framework, as they are outside the control of the HEP.

## 1) Strategy and Finance
Strategy and Finance
Wave | Assumption | Action checklist
Wave 1 - Normal operations | Standard financial regulations, systems and records are in place, and the previous year's audited financial statements are complete. | Develop an integrated suite of real time management reports to share with the Board of Governors, trustees and the HEP senior executives that gives an understanding of the totality of operations: financial and non-financial performance. The suite to include integrated whole organisation income and expenditure, cashflow and balance sheet, with transparent cash reporting and cash management (i.e. budgeted and allocated cash, unallocated operational cash), with integrated reporting of capital projects and transparent treasury management.
| Reporting cycles/timelines are appropriate for the financial structure of the HEP, for example, monthly reports if there are critical covenants and loan conditions to be met. | Establish parameters - tolerance levels appropriate to the HEP's context (short term, medium and long term) for key performance measures: including cash flow, reserves, liquidity, surpluses. Movement outside of agreed tolerance to trigger further immediate explorations and mitigation and reporting, including to the Governing body/trustees. These should complement and comply with the HEP's financial regulations.
| Real-time reports are considered by the governing body and senior executive and include non-financial management reports: tracking of student recruitment by type, student progression and retention, research grant pipeline etc. | Identify HEP's risk profile: the level of risk (internal and external) you are willing to accept when making decisions.
| HEP has mapped and understands the complexity of its organisation. | Scenario plan regularly, as a minimum exploring three scenarios (best to worst case - market exit), from the perspectives of provider, validator and receiver.
Discuss the impact of a potential market exit with local authorities to gain a shared understanding of the impact upon the region and explore potential support that might be available to help mitigate exit.
Map stakeholders and identify those that have a potential financial stake in the institution.
Identify, track and, where possible, quantify:
Funding sources, by type and amount (£), with key terms and conditions - such as repayment, that may have an impact when considering strategic options and HEP refinancing
Current market value of key assets
Value of goodwill
Financial covenants - compliance with set tolerance levels
Secured and preferential creditors: by supply type and amount (£)
Personal guarantees for company debts provided by Trustees or Board Directors: £ and terms
RADIO (Risks Assumptions Dependencies Issues and Opportunities)
Contracts Register that summarises significant long term contracts with terms and conditions of significant impact, including minimum service conditions.
Claims and Disputes, to include all pending or ongoing legal proceedings/investigations, both criminal and civil and the implications: regulatory penalties, best estimate at settlement and £s.
Anticipated and/or actual legal exposure related to environmental, health and safety compliance.
Intellectual property owned or licensed by the HEP, how it is secured and what the implications would be if operation ceases. Where appropriate, ensure there is no termination clause that sees the IP revert to the creator at announcement of exit.
Map endowments and other ring-fenced sources of funding and the conditions that apply/limitations in place.
Wave 2 - Warning signs begin to emerge | Warning signs begin to emerge, for example, tolerances are exceeded and trends are tracking downwards: ratios of liquidity, solvency, profitability, efficiency, and coverage and/or breaches are expected or have occurred of bank covenants, and/or OfS enhanced monitoring is in place. | Confirm what regulators, professional bodies and others will need to be informed and consulted around emergence of warning signs and potential exit.
| Examples of potential warning signs are shared in Appendix A. | COO to inform without delay the Accountable Officer or equivalent of the OfS other regulators/bodies of any circumstance that is having, or is likely to have, a significant adverse effect on the ability of the HEP to deliver its education programmer, research and other related activity, and of any serious weakness, such as a significant and immediate threat to the HEP’s financial position.
Identify critical priorities: the must do and focus, and take action to mitigate risks.
Executive to inform the Board of Governors/Trustees and agree escalation process: frequency of reporting and key delegated powers to ensure actions are able to be taken in a timely manner to mitigate risk.
Develop external and internal comms plan to address each wave of activity. Focus in this wave upon reputational management and mitigation of risk (staff and student loss).
Determine what payments the HEP is committed to over what period (by reference to contract register schedule of commitments) and the potential for renegotiation.
Wave 3 - Contingency planning | Institution contingency plans exist that can be used as a foundation for planning. | Review and invoke appropriate parts of existing contingency plans.
Inform the OfS and other regulatory bodies that HEP is considering it strategic options. Expect the OfS to require an SDP, a detailed exit plan.
Explore strategic options, including sale as a going concern, restructuring the organisation, potential merger or collaborative arrangements with other institutions, locally or internationally. Recognise merger is typically a more costly and longer process than exit.
Develop an acquisition proposal that sets out the HEP as an attractive acquisition: in total or in parts.
Develop external and internal communications plan, to complement and support option appraisal.
Identify the trigger point that would necessitate or make market exit the best option.
Explore refinancing options, including whether assets could be used in a sale and leaseback arrangement.
Quantify cost of a good exit and sources of funding, include costs of legal and financial experts and incentives for staff retention: determine a range (top, middle, bottom).
Identify core staff needed to facilitate a good market exit and provide good support for students.
Determine what might be realised through sale of assets.
Intellectual property rights, determine how the value of these items can be protected and/or realised.
With local authority, explore options to mitigate impact on locality/region.
Freeze recruitment of non-essential posts and non-essential projects.
Review research grants in progress, implications of market exit and make contingency plans.
Review all other projects (inc. estates) in progress and make contingency plans to close.
When market exit trigger point is reached, or if the options appraisal determines market exit is the best option, move to a 'war game footing' and act decisively.
Wave 4 - Preparing to exit the market | Options to continue have been exhausted and the HEP has taken the decision to exit the market. | Inform the OfS and other regulators and appropriate professional bodies that the HEP is preparing for a market exit and intends to implement the SPP and wider contingency plans. Expect OfS to impose a SDP.
| Governing body/trustees have been fully informed and support the decision to exit. | Appoint legal and financial advisors.
Create market exit fund, to facilitate a good and appropriate exit.
| The outline of a high-level Market Exit Project plan is given in Appendix B. | Establish a market exit project team immediately, with governance structure to manage it and associated risks.
| The components of a high-level comms plan is given in Appendix C, and staff actions developed in the Staff and HR tab. | Prepare communications plan - both internal and external, to cover all stakeholders: including students, staff, unions, validating partners, bankers, local authorities, regulators, creditors etc.
Determine if any payments have been made that could be clawed back under insolvency law.
Determine where and how endowments will be transferred in line with donors' wishes.
Determine if the OfS will require repayment of Exchequer interest balances (for public funded capital assets) and if so, on what terms.
Limit spending by signatories/roles, revise delegated authorities.
Remove payment /credit cards.
Prepare information packs for the liquidator/administrator, and regulators, and provide access to records.
Wave 5 - Market exit |  | Implement Wave 4 plans.
| If an Administrator/ Insolvency Practitioner has been appointed, they will take control, but typically will utilise/be informed by the planning undertaken by the HEP in Wave 4. | Typically an Insolvancy Practitioner will within 8 weeks set out plans for the HEP, which will usually need to be agreed by the creditors . The plan will be sent to creditors, staff and regulators.

## 2) Legal & Governance
Legal and governance
Wave | Assumption | Action checklist
Wave 1 - Normal operations | Good governance practices are in place and the CUC code of practice has been applied. It maintains good records of Board minutes and resolutions that include record of challenge and approval of decisions. | Enhance training for governors/trustees around potential market exit and options appraisal.
| Proactive risk management is in place that while including active and critical appraisal and challenge of the Risk Register, is action orientated and focused upon ensuring identified risks do not materialise or are mitigated. | Grant access to independent advice for governors/trustees and senior leaders.
| A culture of openness, ethical leadership, curiosity and constructive challenge is fostered. | Undertake Governing body and trustees capability audits annually and take steps taken to address gaps, ensuring as a minimum, sufficient financial and legal expertise amongst the governing body and Trustees.
Undertake regular reviews of governance.
| There is clear and unambiguous early communication to governing bodies and its committees regarding matters of importance to the whole university. | Appoint a Secretary to the governing body who in carrying out the role of Secretary is solely responsible to the governing body, with a direct reporting line to the Chair of the governing body.
| Papers for governing bodies, critical committees are provided in advance of meetings, to give time for reading and consideration. | Seek assurance annually that all governors/trustees have complied with their fiduciary duties.
Appoint student representatives to the governing body.
Focus upon key dynamic risks at each meeting of the governing body.
Extend pro-active risk management to partners: at minimum a high-level assessment of key risks and mitigation and review of most recent audited financial statements.
Ensure that contracts with essential minimum services variations require continuation of service in event of market exit.
Ensure institutional insurance policies have Directors and Officers liability cover.
Publish the HEP's risk assessment regularly.
Wave 2 - Warning signs begin to emerge |  | Inform and involve immediately the Governing body/trustees of warning signs emerging and potential consequences. Involving them in consideration of strategic options and mitigation and contingency planning.
Agree a process for decision-making outside standard Board meetings, including escalation steps and documentation of all key decisions and rationale.
Explore the governance and legal issues for the HEP of strategic options being considered. Consider appointing a restructuring specialist.
Map multiple institution grants and programmes of work and the impact of potential closure upon IP, staff and funding streams and other commitments.
Explore the effect of the strategic options being considered on the HEP's intellectual capital.
Wave 3 - Contingency planning |  | Seek specialist legal advice on market exit process, appropriate for the HEPs structure: what are its legal obligations and how they may override their regulatory obligations.
Agree timeline for key decisions and milestones.
Plan for the transfer of unresolved complaints and associated data to receiving bodies.
Create flowcharts to guide notification of the OfS, validating partners, and other stakeholders, and initiate the exit process.
Wave 4 - Preparing to exit the market |  | Board to make formal decision regarding market exit and communicate the 'hard' messages to key stakeholders, including students, staff and union, partners and regulatory bodies.
Instigate agreed process for exceptional decision making: delegation, escalation and recording.
Negotiate with suppliers that have essential minimum services variations in their contracts, to require continuation of service.
Determine how payment can be made for essential services during market exit.
Appoint, if necessary, a licensed Insolvency Practitioner.
Agree process for transferring seals and granting access to records to the Insolvency Practitioner.
Wave 5 - Market exit |  | Seek approvals/resolutions required from shareholders.
| If appropriate/needed an Insolvency Practitioner will take control, but will utilise/be informed by the planning undertaken during Wave 4 - preparing to exit the market. | Issue all relevant notices, including insolvency notices if necessary.

## 3) Operational
Operational
Wave | Assumption | Action checklist
Wave 1 - Normal operations | Business continuity plan exists that includes IT and data contingency plans, and a payroll contingency plan that could be applied if needed in an insolvancy procedure. | Develop contingency plans for the different exit scenarios (being explored by Strategy and Finance).
Ensure a student accommodation contingency plan exists that includes private providers' provision, with clarity on student terms and conditions.
Understand what operations and assets can be scaled up, down or mothballed if required and the timelines involved.
Identify contracts and services critical to ongoing operations, minimum service variations and plan for continuation. Avoid contracts having automatic termination of agreements clause.
Identify estate/premises occupancy and terms, including any automatic triggers if Liquidation should occur. For example, if an asset reverts to the original owner on notification of Liquidation.
Ensure there is total clarity about institutionsl GDPR and the implications; this is required for a detailed contingency plan to be effective.
Ensure insurance policies have clarity about cover, or not, for ceasing to be a going concern (and have Directors and Officers liability cover).
Identify key student groups from an operations perspective, prioritised by impact of operations.
Wave 2 - Warning signs begin to emerge |  | Mission critical - ensure IT and other operational contingency plans are robust.
Assess impact of potential strategic change options on key student groups from an operations perspective, prioritised by impact.
Review estate strategy especially to ensure continued access to essential buildings and facilities.
Work through implications of any key operational contractual termination clauses.
Assess implications for leasehold property: for example, what would cause lease to be breached and how could access be maintained.
Assess potential impact upon student residential accommodation and student union premises, and ensure continuation of provision for suitable period.
Identify key suppliers, prioritised by impact of HEI by contract - local and national.
Identify essential core staff needed to continue operations and support student services.
Identify key projects and work-in-progress commitments, seeking opportunities to mitigate risk of early cessation.
Identify potential GDPR issues related to students and course data access by potential providers.
| HESA hold NDAs with most HEPs and therefore might be well suited as a temporary home. | Determine where to hold/transfer student and staff data, if required for an interim period (between HEP exit and transfer to alternative provider).
Wave 3 - Contingency planning |  | Revise business continuity plan in context of market exit plans, include health and safety compliance and risk mitigation.
Ensure students and staff will be able to continue to access essential information: data and systems, to support welfare and continued learning throughout the market exit and for appropriate period thereafter. Factor in additional needs.
Ensure students will continue to be accommodated in residential accommodation throughout market exit and for appropriate period thereafter, for example until transferred to alternative providers.
Ensure essential support for laboratories and research grants can continue until transfer possible or grant work ceases.
Mitigate risk of staff not being available pre and post exit, especially to support students, after exit/campus closure: consider outsourcing contracts and incentivising staff.
Freeze non-essential work and contracts.
Set up enquiry response hub: for staff and students.
Work through implications of timetable review (see academic delivery).
Cost plans and feed into overall budget for closure (see strategy and finance).
Ensure plans align with other areas and feed plans to comms plan for dissemination.
Wave 4 - Preparing to exit the market |  | Create/template GDPR compliant data sharing agreement for data transfer to potential providers.
Agree who will hold student data in interim/transfer period between closure and transfer of students.
Work through implications for existing NDAs and other commercial sensitivities in case of market exit.
Implement contingency plans and curtail operations to critical activities and support, ensuring support for students is appropriately maintained.

## 4) Students
Students
Wave | Assumptions | Action checklist
Wave 1 - Normal operations | Student Protection Plan (SPP) exists. | Review and test SPP and wider contingency plans at least annually, involving student representatives in the process; ensure it is robust and can be applied.
| Student information system is comprehensive and accurate records of progression (assessments and credits), fees and complaints exist. | Ensure clear student redress and compensation schemes exist and are published.
| Clarity exists around who owns student record of students at the validating partner. | Ensure a detailed business continuity plan sits behind SPP.
| Student segmentation is undertaken to give a detailed profile of entire student body. | Require validating partners to provide oversight of their SPPs and have them reviewed by HEP legal advisors.
Clarify/publish responsibilities to students and the legal pathways open to them, given a market exit, including implications for student debt - e.g fees and accommodation.
Publish SPP is a user friendly format making it easily accessible to students and staff.
Map students by location and placement limitations, in addition to other segmentation work being undertaken.
Provide route for students to escalate concerns and issues.
Wave 2 - Warning signs begin to emerge | There is no formal/legal protection for students. Students may be seen as unsecured creditors in an insolvency context, but any duties owed to them do not clearly define duties to support the completion of their studies. | Prioritise student wellbeing with compassionate, transparent, pro-active communication that includes an enquiry route that has an SLA, ensuring the Students' Union (SU) is engaged as soon as possible.
Prioritise existing student complaints and appeals, in particular those with a professionally regulated element.
Identify critical student services: prioritise and plan to deliver continuity of student services throughout a potential market exit.
Recognise that the Student Loan Company has limited flexibility.
Identify implications and options for PGR students, including supervision requirements.
Identify implications and options for students with particular support needs.
Develop proposals for a student support budget and student compensation packages: bursaries and hardship funds, to support students through the process and for a period thereafter. Feed sum required into cost of market exit budget.
Factor in implications for UKVI approved sponsor licence when considering strategic options. Take action to protect status.
Assess the needs of international students, referencing need to meet UKVI requirements.
Wave 3 - Contingency planning |  | Feed the outcomes of actions above to operations lead to ensure alignment of initiatives and a shared understanding of students' needs.
Define student rights realistically in closure scenarios and with reference to the OIA where appropriate. Involve student representatives.
Expect OfS to impose an SDP, to ask for a detailed exit plan.
Tailor the student complaint process to cover market exit, ensuring it will continue/be supported for appropriate period past exit.
Ensure process is in place to ensure student qualifications can be verified in the future: post exit.
Plan student communications, working with SU and aligning and complementing plan with staff and other comms plans.
Develop ways to ensure IT and administrative systems remain operational to support student services.
Wave 4 - Preparing to exit the market |  | Ensure access to finance, housing, and visa advice and support for students and tailored support e.g., bridging modules and travel subsidies.
Assign student liaison (transfer and support) officers during the transition.
Ensure specialist, objective advisors are in place to support students.
Appoint academic advisors to provide personalised support to help students transition to new institutions or programs.
Ensure IT and administrative systems remain operational to support student services.

## 5) Academic Delivery
Academic delivery
Wave | Assumptions | Action checklist
Wave 1 - Normal operations | Student protection plan (SPP) exists. | Map the curriculum and identify programmes/courses that are distinct, where it would be difficult to identify similar provision, for example by quality.
| HEP understands the complexity of its curriculum and academic delivery. | Recognise regional differences and difficulties and consequentially the difficulties that might arise in identifying alternate provision.
| HEP understands fully the viability of its course portfolio, including the cost of delivery. | Integrate planning for potential closure with planning to set up new courses and programmes.
| Cost of curriculum delivery within partners is included in any validation agreement. | Identify potential alternative providers; by programme/course and have 'in principal' discussions: normalising mitigation of market exit planning.
Map the research grants and contracts pipeline: staff deployment to grants and contracts, £s and timelines, critical T&Cs, and associated IP.
| HEP is not under threat of losing professional accreditation(s). | Identify Research partnerships that might, with UKRI approval, be transferred to another provider: critical researchers and associated funding (£s).
| HEP understands and complies with CMA requirements. | Consider student needs (local, commuter, additional needs, etc.) when identifying potential transfer partners.
Map and segment academic roles, including PGR supervisors.
Wave 2 - Warning signs begin to emerge | Warning signs may include enhanced OfS monitoring. | Develop a teach out strategy and supporting plan with timelines, that has tailored academic scaffolding which includes retention of key personnel for continuity (building upon curriculum map).
Develop strategy that includes potential transfer of grants and contracts and key personnel, and makes provision for repayment/claw back of grants.
Initiate conversations about potential market exit and options/implications with key research, grant awarding and other contracting bodies.
Appoint partner liaison officers, adequately trained to help early identification and mitigation of risks.
Determine implications for professional bodies accreditation of a potential market exit.
Identify potential alternative providers.
Share map of curriculum with potential alternate providers.
Identify implications and options for PGR students.
Review timetable and undertake options appraisal, including to reduce reliance on physical buildings and face-to-face delivery, to contain students' time on campus and mitigate risk of poor student experience.
Plan to ensure access to learning resources and virtual learning environments is maintained.
Appoint an internal team to manage teach-out strategy and operations.
Wave 3 - Contingency planning |  | Identify potential alternative providers.
Identify potential alternative PGR supervisors.
Identify potential bodies to take on grants and contracts, transfer of staff.
Develop bridging modules and flexible assessment.
Confirm with accrediting bodies, OfS and other regulators that plans have their approval.
Create and publish new contingency timetable.
Establish credit transfer protocols and clear mechanisms for transferring credits to other HEPs.
Wave 4 - Preparing to exit the market |  | Secure transfer agreements with alternate providers.
Offer flexible credit transfer options and exit awards, where full transfer may not be possible.
Secure alternative supervisors for PGR students.
Develop comprehensive but targeted guidance for receiving bodies, including definition of roles and responsibilities.
Develop transfer agreement templates for use with receiving HEPs.
Share proposals with students, and provide enquiry point (with SLA).
Agree arrangements with research funders and contracting bodies: seeking continuity of funding of grants being transferred.

## 6) Staff and HR
Staff and HR
Wave | Assumption | Action checklist
Wave 1 - Normal operations | HEP has register of all staff by contract type, T&Cs including redundancy terms. | Understand what staff agreements exist that could impact upon how a market exit is dealt with.
| HEP will have a redundancy policy. | Map staff roles to identify critical roles and exposure should staff leave or become unavailable. Address points of weakness through staff and organisation development.
| HEP is engaged positively with its unions and involves them routinely in strategic planning. | Track open grievances and/or HR disputes pending and the potential implications.
Complete Exit interviews trend analysis, share with the governing body, to inform strategic considerations.
Understand the consequences of market exit upon pension schemes specifically HEP (or sector) pension schemes: associated liabilities and responsibilities to staff.
Provide route for staff to escalate concerns/issues.
Wave 2 - Warning signs begin to emerge |  | Inform and engage unions and Governors/trustees in the exploration of strategic options.
Recognise retention of key staff is critical to success. Identify key staff whose departure would be critical and develop contingency plans.
Consider and quantify what incentives might be offered for critical staff to stay through the exit and beyond where needed.
Engage with Pension schemes to understand implications of market exit (for the HEP and typical groups of staff) including potential cessation costs and the ability of staff to transfer pensions.
Determine, at a high-level, TUPE and redundancy implications if exiting the market.
Determine HMRC liabilities and potential status as creditor.
Cost plans and feed into overall market exit budget (see Strategy and Finance).
Identify all the bodies that might help staff to find alternative jobs.
Communicate position to staff and ensure staff and student communications are aligned and complementary.
Wave 3 - Contingency planning |  | Engage with potential alternative providers to assess opportunities for staff to be transferred.
Agree with pension providers approach to exit: having determined implications for HEP and staff.
Offer incentives for critical staff to stay through the exit period: for example, fixed term contracts and financial awards.
Create communication plan for all stakeholders, tailor to needs of stakeholder groups: including staff and by group of staff.
Ensure student and staff communications and incentives are aligned and complementary.
Develop support schemes for staff that will continue/be available throughout and after the exit process.
Prepare templates and guidance notes for various staff members at different stages of market exit process.
Wave 4 - Preparing to exit the market |  | Keep staff and unions informed of process and implications.
Activate staff support schemes.
Provide staff liaison officers to support transfer or exit of staff.
Commission bodies to help staff find alternate employment.
Provide pension advice for staff on the implications of market exit on pensions. Provide access to personalised advice, utilising and coordinating with pension providers.
Track critical staff departures and implement contingency plans.

## Appendix A Warning signs
Appendix A
Early warning signs to be monitored
This list is illustrative: it is not an exhaustive list.
1. Financial Health
Cash flow falls below tolerance levels: monthly, quarterly, annually, 5 and 10 year horizons
Liquidity ratios are outside of tolerance levels
Budgeted and forecast income and expenditure concerns - surplus not achieved and outside tolerance levels
Student recruitment and tuition fee income fall outside accepted tolerances: in year and over next 5+ years
Audit report (internal and external) outcomes and warnings
Failure to meet bank covenants: actual or projected up to 5+ years
Bank reduces institution's credit rating
Cost of borrowing increases beyond planned, outside of tolerance levels
Bank of England base rates increase beyond forecast and above tolerance levels
Significant increase in cost of energy
Rate of inflation exceeds expected, above tolerance levels
2. Academic Performance
Student progression, retention, and completion rates fall - outside of expected rates
External examiner reports and quality assurance outcomes show a decline in standards: across institution and/or by specific programmes
OfS enhances monitoring
TEF and KEF results fall and are out of line (negatively) with sector
Institution compares poorly to sector norms and KPIs
3. governance
Board effectiveness reviews highlight deficiencies
Insufficient financial and legal expertise on governing bodies
Increase in concerns raised by stakeholders, including staff and students
4. Student Feedback and Engagement
Student satisfaction surveys trends decline and complaints increase
Lack of engagement with Student Union and student representatives
5. Partner and Validation Risk Assessment
Due diligence on academic and commercial partners highlights issues
Partner performance and compliance fall
Partners have no clear exit strategies and contingency plans

## Appendix B Project Plan outline
Appendix B
Market Exit Project Plan - high-level components
Actions | Responsible person
Appoint a Project Manager
Create a Project Plan and timeline
Agree governance model for project, terms of reference and meetings with the Governing Body
Identify necessary staff to work on project
Create a stakeholder map for the project (utilising university map)
Obtain legal advice
Identify and mitigate reputational risks (using Comms plan)
Develop communication plan, working with Board, students, staff and unions: agree messaging and statements including for public announcements
Agree communication plan and designate key points of contact, incorporating an enquiry management process, for distinct stakeholder groups
Identify what support or response is available/ expected from public authorities and regulators, including OfS
Create an escalation plan with delegated authorities so that the project manager has the necessary authority
Agree enquiry management process, including escalation process
Collate and disseminate lessons learned from the process
Multiple specialist teams will be required to work on aspects of the project, including for example:
governance team to set out and ensure compliance with the process and timelines required by law
Project Management Office
Student and staff support teams, to work through the effects on students and staff
Ops team to evaluate and identify options for the minimum viable services that will be required to maintain an operational institution
Finance team to determine the fiscal options and possible alternatives that could be negotiated with funders
Communication team to develop messaging and support delivery to agreed timelines
Procurement team to negotiate changes in suppliers' contracts, to mitigate against automatic cessation of services upon exit.

## Appendix C Comms plan
Appendix C
Communication Plan Components
1. Communication Planning
Develop a crisis communication strategy for internal and external audiences with pre-approved messages and timelines
Expect leaks and develop a contingency plan
Identify key audiences (students, staff, partners, regulators) and preferred communication channels
Make communications compassionate as well as transparent and timely
Establish dedicated enquiry centres: helplines, email address, and FAQ pages
Schedule regular updates, even when no new information is available
Involve student representatives in shaping and reviewing communications
2. Wellbeing Support
Signpost to counselling and mental health services
Set up peer support groups and wellbeing drop-ins
Train staff in trauma-informed communication
Communicate available support services clearly and regularly
3. Student Support
Assign academic advisors to support students through transitions
4. Financial Assistance
Provide clear guidance on tuition refunds, hardship funds, and student finance
Communicate financial support options transparently and promptly
5. Roles and Responsibilities
Define roles for communication leads, academic advisors, finance officers, and wellbeing coordinators
Assign a senior responsible officer to oversee the closure response
Ensure all staff are briefed on their responsibilities and escalation procedures
Maintain a contact directory for internal and external stakeholders